Contingency Plan List:

Pre-prod:
Focus Group - Problems with sourcing people
- Use different social media to source people from instead (Reddit, Twitter, etc.)
- Source people offline(?)

Interviews - No response from emails sent to Bute Street Film Festival
- Email Akua & Gabrielle ‘directly’ through both of their company’s email addresses
- Attend the event and ask them a question through their panel discussion / ask if they’d be willing to be interviewed directly

Photoshoot - Scheduling issues
- Do the photoshoot during a production week instead of pre-production
- Ask Tasha for photos of herself to use in the magazine if she can’t meet in person

Time management – three weeks to finish everything
- Allocate to finish a section of pre-production by the end of each week
week 1: writing/documents – research for articles, writing documents & sourcing people for magazine designer/focus group
week 2: write article drafts & interview questions, conducting interviews
week 3: mock-ups, article final

Prod:
Software - Crashes or 2022/2023 version confliction
- Automatically (or manually) save every minute
- Work on 2023 version in a booked classroom instead of the library

Data loss – Due to crashes or losing my hard drive
- Save onto both my hard drive & USB drive 

Magazine Designer/Focus Group - Lack of responses
- Send them my work in progress files at the end of Friday
- Send reminders at the end of each day if they still haven’t responded yet

Schedule for Contributors – Schedule conflicts 
- Schedule interview & photoshoot for Tasha
- Set up a schedule for when I’ll be sending files to the focus group & magazine designer

Post-prod:
Printing - Unable to print
- I’ll send my magazine odd to printing at the end of the first week of post-production, the second week of post-production will be allocated to fixing any issues I have with printing